## Slide 1: ONAP Cadence Release Proposal (v4)
Catherine Lefevre, ONAP TSC Chair

## Slide 2: Traditional ONAP Timeline
OPEN-O
8w 4w 3w 4w 2.5w 2w 3w 1w
From Amsterdam to Dublin – ~28 weeks
M3
APIs
Freeze
Sign Off & Release
M4
Code
Freeze
M2
Functionality
Freeze
M1
Planning
Freeze
Scope Def. & Design
Development
RC2
Tests and bug fixes
RC0
RC1
M0
Kick-Off
Use Cases
Functional Requirements
Non-Functional Requirements (S3P, CICD, Optimization, Bug Fixes, etc.)
POCs

## Slide 3: ONAP Timeline Evolution – From Dublin to El Alto
Dublin
Sign Off & Release
M4
Code
Freeze
RC0
RC1
El Alto (Dev/Test Engagement)
6/13
8/29
“Reduce Internal Debt” (Every 4 ONAP releases)
Refactoring
JIRA Backlog Reduction (defects, etc.)
Vulnerability issues
Test Coverage including jS
Test Automation & CI/CD pipeline
Deployment procedure
Documentation
etc.
7w -> 4w 4w -> 6w 3w
Frankfurt
6/13
9/5
Scope Def. & Design
M1
Planning Freeze
M0
Kick-Off
Sign Off & Release
M4
Code
Freeze
M2/M3
Functionality/API
Freeze
RC2
RC1
RC0
Development
Tests and bug fixes
F1 Release Candidate?
El Alto Release
Frankfurt
Release
7/18
E1 Release Candidate?
RC2
10/3
11/14
12/5
1/16
2/6
2/13

## Slide 4: ONAP Timeline Evolution – Release G
G1 Candidate
G2
Gx
10 W
Dev G1
Test G1
Rel. G1
Limited Code Change (Max. 4 weeks)
No or limited cross-applications dependency
Non-Functional Requirements (Security/Vulnerability issues, Code Optimization, Sev2 Defect Backlog Reduction, etc.)
PTL Enhancements
Documentation Enhancements
Gx Release Candidates
included in G Release until Release Code Freeze (M4)
Def. G1
Dev G2
Test G2
Rel. G2
Def. G2
Dev G3
Test G3
Rel. G3
Def. G3
5 W
5 W
...
@Frankfurt RC0? RC1?
Create Frankfurt Branch and Kick-Off G Candidate Release ?
7w 1w 4w +3w -> 4w 4w ->6w 3w 2w 3w 1w
G Release
Sign Off & Release
M4
Code
Freeze
M2/M3
Functionality/API
Freeze
M1
Planning
Freeze
RC2
RC0
RC1
M0
Kick-Off
G1
G2

## Slide 5: ONAP Timeline Evolution Pre-Requisites & Risks
OPEN-O
Pre-requisites:
Identify Small Content (<4 Weeks Development)
3 Development/Testing Environments (including 1 for Maintenance Release)
Review tag strategy i.e. No Tagging until verify jobs are successful
Increase container storage
Same rules as Release i.e. Sonar Test Coverage, License/Vulnerability, Automation Testing etc.
Risks:
Maintenance vs Release Candidates vs Main Release
Code conflict between Main and Release Candidates
Dev/Testing capacity
Additional merging activities ?